CONSTRUCTION COMMITTEE

# FEBRUARY 20, 2002

| PROJECT: | METRO RED LINE, SEGMENT 3, NORTH HOLLYWOOD EXTENSION |
| --- | --- |
| CONTRACT: | CO326, UNIVERSAL CITY STATION FREEWAY OVERCROSSING AND SITE RESTORATION BRUTOCO ENGINEERING AND CONSTRUCTION |
| ACTION: | CONTRACT MODIFICATION IN THE AMOUNT OF $1,065,120 AND APPROVE AN INCREASE IN AUTHORIZATION FOR EXPENDITURE IN THE AMOUNT OF $2,765,000 |

RECOMMENDATION

- Authorize the Chief Executive Officer to execute Change Order No. 73 to Contract No. C0326, Universal City Station Freeway Overcrossing and Site Restoration, with Brutoco Engineering and Construction, Inc. (BEC), to pay for extended overhead costs for  compensable delays in the contract completion date between December 1999 and February 2001, in the amount of $1,065,120, increasing the Total Contract Value from $33,690,696 to $34,755,816; and

- Approve an increase in the Authorization for Expenditure (AFE) to Contract No. C0326 to provide funding for Change Order No. 73 and for 26 other changes issued or executed within the Board-delegated authority in the amount of $2,765,000, increasing the total current Contract No. C0326 AFE amount from $33,861,816 to $36,626,816.

Within Construction Committee authority:	  Yes	  No		  N/A

BACKGROUND

Completion of Contract No. C0326 has been delayed by the following factors:

- Fabrication of bridge structural steel as a “fracture critical member.”  This was not expressly required by the C0326 Contract drawings, but was raised as a concern by BEC’s steel subcontractor, based upon its familiarity with CalTrans bridge requirements.  A decision on this issue delayed subcontractor acquisition of this long-lead item.  In order to avoid further delays, the MTA directed BEC

- by contract modification to have the steel fabricated and tested to “fracture critical” specifications.  Subsequent criteria review and analyses, and confirmation by CalTrans, determined that the steel need not be fracture critical; however, it had been procured, fabricated and tested to meet that standard. There was an overall schedule impact in resolving this issue and complying with the contract modification.

- Ambiguities in the structural steel welding submittal requirements and Caltrans submittal and review requirements.  The Contract was not clear as to whether BEC’s structural steel subcontractor was required to submit a quality control plan prior to steel fabrication.  In accordance with CalTrans quality assurance requirements, and in order to avoid concerns about weld quality, the MTA required advance submittal of a quality control plan.  BEC’s compliance with this requirement delayed fabrication of the structural steel.

- Delays to construction of concrete support structures.  These were caused by productivity impacts of pile welding requirements and testing; resolution of design inconsistencies in contract drawings; resolution of specification ambiguities; differing site conditions; and additional requirements imposed by the City of Los Angeles and CalTrans.

Staff determined that the above delays are compensable, and that the Contractor is entitled to a change under the terms and conditions of the Contract.

FINANCIAL IMPACT

Original Contract Award			$27,891,956

Current Cumulative Contract Value		$33,690,696

This Action					$  1,065,120

New Cumulative Contract Value		$34,755,816

The funds for this action are available within the Board approved Metro Red Line, Segment 3, North Hollywood Extension budget of $1,313,848,000.  This recommended action will increase

the current Contract No. C0326 Total Contract Value by $1,065,120, and is included as part of the current Segment 3 budget forecast.  The current status of the contract, including the impact of this recommended action, is shown in Attachment 1.  This recommended action does not impact the Fiscal Year Budget or the Sources of Funds, either in the fiscal year, or over the life of the project.

Potential for Cost Recovery:		  Yes         No        N/A

ALTERNATIVES CONSIDERED

The MTA Board may reject this action; however this will prevent compensation of the Contractor for additional costs merited by staff.  The Contractor may pursue other remedies, up to and including litigation.

ATTACHMENTS

| A. | Procurement Summary |
| --- | --- |
| B. | Table of Changes within Board-Delegated Authority |
| 1. | Contract Value Status Summary |

Prepared by:	Robert P. Sechler, Senior Contract Administrator

Olga Cervantes, Contract Administration Manager

__________________________________

DENNIS S. MORI

Interim Executive Officer, Construction

__________________________________

ROGER SNOBLE

Chief Executive Officer

BOARD REPORT ATTACHMENT A

PROCUREMENT SUMMARY

Contract No. C0326 for Universal City Station

Freeway Overcrossing and Site Restoration

|  | Contract Number: C0326 |
| --- | --- |
|  | Recommended Vendors: N/A |
| 3. | Cost/Price Analysis Information: See Attachment A-1 |
|  | Bid/Proposed Price: See Attachment A-1 | Recommended Price: See Attachment A-1 |
|  | B. Details of Significant Variances are in Attachment A-1 |
|  | Contract Type: IFB, Fixed Price |
|  | Procurement Dates: |
|  | A. Issued: N/A |
|  | B. Advertised: N/A |
|  | C. Pre-proposal Conference: N/A |
|  | D. Proposals Due: N/A |
|  | E. Pre-Qualification Completed: N/A |
|  | F. Conflict of Interest Form Submitted to Ethics: N/A |
|  | Small Business Participation: See Attachment A2 |
|  | A. Bid Goal: See Attachment A2 | Date Small Business Evaluation Completed: See Attachment A2 |
|  | Small Business Commitment: See Attachment A2 |
|  | Invitation for Bid/Request for Proposal Data: |
|  | Notifications Sent: N/A | Bids/Proposals Picked up: N/A | Bids/Proposals Received: N/A |
|  | Evaluation Information: |
|  | A. Bidders/Proposers Names: N/A | Bid/Proposal Amount: N/A | Best and Final Offer Amount: N/A |
|  | B. Evaluation Methodology: N/A |
|  | Protest Information: |
|  | A. Protest Period End Date: N/A |
|  | B. Protest Receipt Date: N/A |
|  | C. Disposition of Protest Date: N/A |
|  | Contract Administrator: Barbara Gatewood | Telephone Number: 922-7317 |
|  | Project Manager: Roger Dames | Telephone Number: 922-7280 |

BOARD REPORT ATTACHMENT A-1

PROCUREMENT HISTORY

Contract No. C0326 for Universal City Station

Freeway Overcrossing and Site Restoration

# Background on Contractor

Contract No. C0326 is a fixed price federally funded procurement for the Universal City Freeway Overcrossing and Site Restoration.  On October 18, 1999, Contract No. C0326 was awarded to Brutoco Engineering and Construction, Inc. (BEC), in the amount of $27,891,956.  The Notice-to-Proceed was issued on December 23, 1999 with a contract completion date of March 17, 2001. The current forecast completion date is in June 2002; however, MTA Construction Management is pursuing alternative construction methods to improve upon this schedule.

B.  Procurement Background

On June 20, 2001, Brutoco Engineering and Construction submitted a formal certified proposal for extended overhead resulting from delays.  Staff prepared an Independent Cost Estimate,  technical analysis, and Time Impact Analyses.  Fact Finding Sessions were held in November 2001.  As  a result of fact finding, Brutoco reduced its original claim for time extension and extended overhead. Staff prepared negotiating positions, based upon evaluation of reasonable, allocable and allowable costs incurred from the delay.  Negotiations were held in December 2001, and agreement was reached on days of time extension and amount of extended overhead.

C.  Evaluation of Proposals

The MTA Project Office, Office of Procurement, and County Counsel have reviewed the facts underlying this change and concur that it has been merited under the terms and conditions of the Contract and Public Utilities Code §130243.  The Management Audit Services Department (MASD) has performed the required audit of the Change Order, and all issues have been resolved.

# D.  Cost/Price Analysis Explanation of Variances

The recommended amount has been determined to be fair and reasonable, based upon fact finding, clarifications, cost analysis, and pre-award audit performed by the Management Audit Services Department (MASD).  The Proposal, Audit and Estimate used different assumptions for the various cost elements.  Development of the Negotiated Amount and reconciliation of the Contractor’s Proposal, MASD Audit, and MTA Estimate reflected actions ranging from decreasing the amount for disallowed markups, unsupported labor, material and equipment, reduction of overhead daily rates, and reduction of days of time extension, to increasing the amount for supported labor, material and equipment costs, recalculation of daily overhead rates

using approved methodology, and contractor support of time extension.  The Negotiated Amount is a $830,835 (44 percent) decrease from the Contractor’s Proposed Amount.

| PROPOSED AMOUNT | MTA ESTIMATE | NEGOTIATED AMOUNT |
| --- | --- | --- |
| $1,895,955 | $634,620 | $1,065,120 |

BOARD REPORT ATTACHMENT A-2

SMALL BUSINESS PARTICIPATION

AND LIST OF SUBCONTRACTORS

Contract No. C0326 for Universal City Station

Freeway Overcrossing and Site Restoration

Small Business Diversity (SBD) established a Disadvantaged Business Enterprise (DBE) participation goal of 18.59%. The contract was awarded October 18, 1999 and is approximately 84% complete.  Current DBE attainment1 based on the relevant contract amount2 is 21.03%.

Current DBE participation3 based on the total actual amount paid-to-date to prime is 23.79%.  The original DBE subcontractors have performed on the Contract as listed.

Original Award Amount			 $          27,891,956

Relevant Contract Amount2		 $          31,872,716

Total Actual Amount Paid to Date to Prime	 $          24,647,192

| Subcontractor | Commitment | Current Attainment 1 | Current Participation3 | Current Status |
| --- | --- | --- | --- | --- |
| Calmex Engineering | 3.07% | 1.81% | 2.05% | Performing |
| Bali Construction | 4.00% | 3.37% | 3.81% | Performing |
| Ramirez Masonry, Inc. | 0.67% | 1.26% | 1.42% | Exceeding |
| G & C Equipment | 10.76% | 14.37% | 16.26% | Exceeding |
| D & N Concrete Pumping | 0.09% | 0.22% | 0.25% | Exceeding |
| TOTAL | 18.59% | 21.03% | 23.79% | Exceeding the Goal |

1Current Attainment = Total Actual Amount Paid-to-Date to Subs  ÷ Total Relevant Contract Amount

2Relevant Contract Amount = Original Contract Value + Contract Cost Modifications affecting DBE or SBE Scope of Work

3Current Participation = Total Actual Amount Paid-to-Date to Subs ÷ Total Actual Amount Paid-to-Date to Prime

# BOARD REPORT ATTACHMENT B

# TABLE OF CHANGES EXECUTED

# WITHIN BOARD-DELEGATED AUTHORITY

Contract No. C0326 for Universal City Station

Freeway Overcrossing and Site Restoration

| CO No. | Description | Amount |
| --- | --- | --- |
| 1.00 | CN 8.00/01 Upgrade Structural Steel Girders |  |
| 15.00 | CN 4.01 Electrical Tie-in From C0321 Station |  |
| 44.00 | CN 31 Revise Lankershim Median and Curbline Drawings |  |
| 51.00 | CN 43 Revise Work at Lankershim and Bluffside |  |
| 54.00 | CN 128 Revised Select Backfill Limits at MSE Walls 1,2,7,8 & 9 |  |
| 55.00 | Cn 7.00/01 Revisions to Retaining Wall at Campo de Cahuenga |  |
| 56.00 | CN 15.00 Caltrans Conditions of Permit |  |
| 57.00 | CN 49 Provide Resources to Stabilize Soil |  |
| 58.00 | CN 60 Power Service Relocations at County Park-and-Ride |  |
| 59.00 | CN 81 Raising Station Appendages to Grade |  |
| 60.00 | CN 90 Additional K-Rail |  |
| 61.00 | CN 104.01 Increase Height of Bluffside Wall |  |
| 62.00 | CN 123.01 DWP Water Line Protection Structure |  |
| 63.00 | CN 132.00 Removal of Concrete Slab in Pavement Struct. Section |  |
| 64.00 | CN 14 Bus Plaza Alignment Grading and Drainage Revisions |  |
| 65.00 | CN 21 Delete Vineland Avenue Median |  |
| 66.00 | CN 116 Drainage Modifications |  |
| 67.00 | CN106 Additional Reinforcing Work |  |
| 68.00 | CN 33 Revised Street Lighting Drawings |  |
| 69.00 | CN 23.01 Revised Wall Along Bluffside Drive |  |
| 70.00 | CN 42 Bid Item Quantity Adjustment – Concrete Manhones |  |
| 71.00 | CN 44 Further Revisions to Interim Traffic Signaling |  |
| 72.00 | CN 83 Trim Grass/Weeds at Park-and-Ride Lot |  |
|  | WACN 101 Electrical Modifications on CalTrans ROW |  |
|  | WACN 102 Increase Bid Quantity for Item 2528 Conc. Sidewalk |  |
|  | WACN 119 Revisions for MSE Retaining Walls on City ROW |  |
|  | TOTAL | $1,729,965 |