## CONSTRUCTION COMMITTEE

NOVEMBER 20, 2002

###### PROJECT:	LOS ANGELES RAIL CAR PROJECT

ACTION:	PROJECT BUDGET INCREASE IN THE AMOUNT OF $13,895,329

### RECOMMENDATION

Approve an increase in the Los Angeles Rail Car Project Budget in the amount of $13,895,329 increasing the total project budget from $201,400,000 to $215,295,329.

Within the Construction Committee Authority: Yes     No     N/A

### BACKGROUND

The Los Angeles Rail Car Project is comprised of three major cost elements,

1.)  The P2000 Los Angeles Standard Light Rail Vehicle Contract, 2.) Consultant Services to support the vehicle contract, and 3.) MTA staff support.

For some time the Project Team has been concerned that insufficient funds remained in the Project Budget to complete the required activities.  The P2000 Contract which constituted 90% of the project budget was three years behind schedule and appeared to be slipping farther.  This slippage not only requires additional MTA staff support but also additional consultant services during the lengthy commissioning process to accept the vehicles.  Moreover, technical changes and additions by the MTA including the between car barriers, and other changes to enhance vehicle performance, have been incorporated.  Further, Siemens, the Vehicle Contractor has filed claims for approximately $2,750,000.

Earlier this year, during the FY03 budget process, staff identified in the forecast to complete for the project, that the $201.4 million project budget would be exceeded.  Additional Prop C funds were budgeted to cover the increase realizing that Board approval would be required once the extent of the increase was determined.

Now, the status of the P2000 Contract is at a point where completion costs can be reasonably estimated.  Currently, delivery of the vehicles is on-going and 42 vehicles (as of 10/17/02) have been conditionally accepted.  Eight additional vehicles are on site and the two remaining cars should arrive on site by December.

Commissioning testing of the vehicles is continuing and all remaining vehicles are scheduled to be accepted by the MTA no later than December 31, 2002.

### Based upon the above, an estimate to complete was prepared which indicates an additional $13,895,329 is required to complete the project.  That amount represents a 2.2% increase in the vehicle contract and a 6.9% increase in the project budget over the 10 year life of the project.

### The estimate to complete includes all effort, changes and claims identified to date.  It takes into consideration the 22 car reduction authorized by the MTA Board for a reduction of $45,528,516 to the P2000 contract.  Also included are Economic Price Adjustment (EPA) payments of $12,256,374 which were made in accordance with the EPA Contract Provision CP-4, which was approved by the Board as part of the original P2000 contract.  Approval by the Board of the recommended project increase will also serve to document the 22 car reduction credit and ratify the EPA payments so that price adjustments can be made to the P2000 contract.  See attachments A, B, C, D, E, and F for details.

### FINANCIAL IMPACT

The funding of $13,895,329 for this action is included in the FY03 Budget in Project Number 800150, and Cost Center Number 8510.  The Project increase is funded with Prop C Funds.  Since this is a multi-year project, the cost center manager and Executive Officer will be accountable for budgeting the cost in future years.

ALTERNATIVES CONSIDERED

The MTA Board may reject this Project Budget Increase, which will result in insufficient funds to complete the project.  Staff does not recommend this alternative.

ATTACHMENTS

Attachment A:		P2000 Project Budget

Attachment B:		Contract No. P2000 Estimate to Complete

Attachment C:		Contract No. P2000 Executed Changes

Attachment D:		Contract No. P2000 Pending Changes

Attachment E:		Contract No. P2000 Pending Claims

Attachment F:		Consultant Costs

Prepared By:	Nick Brown, Director Systems Integration

Tom Butler, Contract Administrator

___________________________

Dennis S. Mori

Interim Executive Officer, Construction

____________________________

Roger Snoble

Chief Executive Officer

Description of Attachments

Attachment A

Summary of Estimate to Complete for the Los Angeles Rail Car Project versus the current Project Budget.

Attachment B

Summary of Estimate to Complete including explanation of Economic Price Adjustments for the P2000 Contract.

Attachment C

List of Executed Change Orders for the P2000 Contract.

Attachment D

List of Pending Changes (increases and decreases) for the P2000 Contract.

Attachment E

List of Pending Claims for the P2000 Contract.

Attachment F

List of Consultant costs for the Los Angeles Rail Car Project.

|  | Original Budget (74 cars) | Current Budget (52 cars) | Estimate At Completion (EAC) (52 cars) | Variance EAC Versus Current Budget (52 cars) |  |
| --- | --- | --- | --- | --- | --- |
| Vehicle Contract | $215,370,314 | $170,015,845 | $173,691,112 | $3,675,267 | NOTE: 1 |
| Consultant (LTK) | $6,881,976 | $7,124,891 | $15,169,895 | $8,045,004 | NOTE: 2 |
| Consultant (Others) |  |  | $2,593,338 | $2,593,338 | NOTE: 3 |
| MTA Staff | $7,432,835 | $4,407,691 | $6,500,000 | $2,092,309 | NOTE: 4 |
| EPA | $12,432,237 | $10,741,984 | $12,256,374 | $1,514,390 | NOTE: 5 |
| Automatic Train Protection System (ATP) |  |  | $3,100,000 | $3,100,000 | NOTE: 6 |
| 5% Contingency | $12,105,870 | $9,109,589 |  | ($9,109,589) | NOTE: 7 |
| Allowance for changes |  |  | $1,984,610 | $1,984,610 | NOTE: 8 |
|  | $254,223,232 | $201,400,000 | $215,295,329 | $13,895,329 |  |
| Explanation for Variance |  |  |  |  |  |
| Note 1: See Attachments B, C, D & E for details. |  |  |  |  |
| Note 2: See Attachment F for details. |  |  |  |  |
| Note 3: Other Consultants completed 1992-1996. |  |  |  |  |
| Note 4: Agency costs increased due to contract delay. |  |  |  |
| Note 5: EPA payments completed 1994-1998. |  |  |  |  |
| Note 6: ATP was originally included in Pasadena Budget but was transferred to the P2000 project. |  |
| Note 7: 5% contingency calculated on total of Vehicle Contract, |  |  |  |
| Consultant (LTK), MTA Staff and EPA. |  |  |  |  |
| Note 8: Allowance for future MGL, PGL and Operations requested changes. |  |  |

| Awarded Contract Value |  | $215,370,314 |
| --- | --- | --- |
| Total Executed Change Orders |  | ($1,290,981) |
| See Attachment C for Details |  |  |
|  | Current Contract Value | $214,079,333 |
| Total Pending Changes |  | ($43,033,404) |
| See Attachment D for Details |  |  |
| Total Potential Claims |  | $2,645,183 |
| See Attachment E for Details |  |  |
|  | Pending/Potential Contract Value | $173,691,112 |
| Total Economic Price Adjustment |  | $12,256,374 |
| See Note Below for Details |  |  |
|  | Total Forecast Contract Value | $185,947,486 |

Note: Economic Price Adjustment

The prices in the P2000 contract are fixed prices in 1993 dollars and are subject to the

Economic Price Adjustments (EPA) clause, Provision CP-4 of the contract.  That

provision, which was approved by the Board as part of the original P2000 contract,

provides for quarterly adjustments in price, upward or downward, based upon indices

published by the United States Department of Labor and the United States Department

of Commerce.  The purpose of the EPA is to limit the Contractor's risk and reduce the

MTA's overall costs for unanticipated increases in labor and material.  MTA's interests

are also protected should prices for labor and material fall.  Quarterly adjustments in

price based on 52 vehicles have been calculated and payments made to Siemens

over the life of the contract for 19 quarters ending in 1998, the original contract

completion date.

| Executed Change Orders |
| --- |
| CO No. | Amount | Change Title |
| 1 | $0 | Misc. Wording Changes |
| 2 | ($1,000,000) | Add Options/Testing, Location Change |
| 3 | $71,656 | Deletion/Addition Technical Requirements |
| 4 | $9,794 | Drivers Cab Seat Option |
| 5 | ($15,601) | Change in Specified Battery Requirements |
| 6 | ($5,000) | Sale of ATPDP Bench Test Unit |
| 7 | $0 | Sandbox Relief |
| 8 | $0 | Additional Specification Corrections/Clarifications |
| 9 | $0 | Technical Correction/Clarifications, |
|  |  | Technical Spec Lang. Chngs |
| 10 | $93,710 | Wheel Flange Lubricators |
| 11 | ($114,795) | Vehicle Design Conformance Tests Relief |
| 12 | $0 | Roof Mat Edges Ret. Mod |
| 13 | $0 | One Piece Windshield |
| 15 | $0 | Modification to Radio Antenna and Mounting |
| 16 | $0 | Specification Changes |
| 17 | $44,024 | Various Communications Changes |
| 18 | ($337,800) | Delete Between Car Warning Device |
| 19 | ($109,765) | Coupler Speed Modification |
| 20 | $53,772 | Change in Exterior Stripes/Graphics |
| 21 | $0 | Delete Silent Alarm/Listen in Features |
| 22 | ($79,285) | Spin/Slide Modification |
| 23 | $46,787 | Change in Flip-up Seat Design |
| 24 | $0 | Technical Wording Changes |
| 26 | ($14,387) | Revised Spare Parts and consumables for P2000 |
|  |  | Vehicles |
| 28 | $0 | Administrative Changes |
| 29 | $23,807 | Bypass Indicator Panel Modification |
| 30 | $0 | Progress Payment Retention Modification |
| 31 | $42,102 | ATP Coil Mounting Modification |
| Total | ($1,290,981) | Reduction |

| Pending Changes/Increases |
| --- |
| CN No. | Amount | Change Title |
| **34 | $245,005 | Destination Sign Modification |
| 44 | $150,000 | EMI Bypass & MSCB Counter Mods. |
| 45 | $1,114,125 | Between Car Barrier System |
| **52 | $28,925 | Communication Control Head |
| 58 | $90,000 | Traction Inverter Mod. For Pasadena Cars |
| 59 | $99,832 | Spin/Slide Timing Mod. |
| 60 | $154,000 | Brake Cut-In/Out Mod. |
| **64 | $101,756 | EMI Detector Settings Mod. |
| 65 | $99,577 | Lamp Test |
| **67 | $52,795 | Modify the BFM & M5 Cycles |
| **68 | $73,500 | Modify the Train control Unit Detection Cycle |
| **69 | $225,000 | Seat Change Out for the last 26 cars |
| 70 | $24,000 | ATC Bypass Change |
| TBD | $236,597 | Spin/Slide Enhancements |
| Total | $2,695,112 | Increase |
| Pending Changes/Reductions |
| CN No. | Amount | Change Title |
| **29 | ($45,528,516) | Car Reduction Option |
| 57 | ($200,000) | Subsystem Isolation |
| Total | ($45,728,516) | Reduction |
|  | Net Reduction | ($45,728,516) |
|  | Net Increase | $2,695,112 |
|  | Net Change | ($43,033,404) Reduction |
| **Negotiated Value |

|  | Pending Claims |
| --- | --- |
| ** | $593,278 | Half Second Emergency Brake |
|  | $201,905 | Sander Hose |
|  | $1,500,000 | Invalid Trainlines |
|  | $350,000 | MBL/MGL Mode Change |
|  | $2,645,183 |  |
|  | **Negotiated Value |  |

| 1. Various Consultant Support during 1992-1996 |  |  | $2,593,338 |
| --- | --- | --- | --- |
| including proposal/pre-contract activity |  |  |  |  |
| 2. LTK Engineering Contract No. E0350 |  |  |  |  |
|  | Award/Change Dates | Title | Period of Performance | Dollar Value |  |  |  |
|  | Jun. 94 | Original | thru Dec. 97 | $6,512,994 |  |  |  |
|  | Jun. 95 | New Scope | thru Dec. 99 | $4,918,147 |  |  |  |
|  |  |  |  | $11,431,141 |  |  |  |
|  | Feb. 99 |  | Separate Task | $28,031 |  |  |  |
|  |  |  |  | $11,459,172 |  |  |  |
|  | Jun. 00 | Time Extension | thru Dec. 01 | $2,377,594 |  |  |  |
|  |  |  |  | $13,836,766 |  |  |  |
|  | Feb. 02 | Time Extension | thru Apr 02 | $300,000 |  |  |  |
|  |  |  |  | $14,136,766 |  |  |  |
|  | Apr. 02 | Time Extension | thru Nov. 03 | $1,033,129 |  |  |  |
|  |  |  |  | $15,169,895 |  |  |  |
|  |  |  | Current LTK Contract Value |  |  | $15,169,895 |
|  |  |  | Total Consultant Value |  |  | $17,763,233 |
| Note- LTK extensions due to extended |  |  |  |  |
| duration of P2000 Contract. |  |  |  |  |  |
| All changes were approved by the MTA Board. |  |  |  |  |