## CONSTRUCTION COMMITTEE

## JANUARY 15, 2003

#### SUBJECT:	CLOSEOUT OF METRO RED LINE

SEGMENT 2 AND 3 CONTRACTS

ACTION:	RECEIVE AND FILE

RECOMMENDATION

Receive and file November 2002 Metro Red Line Segment 2 and 3 closeout status.

# ISSUE

This is an update on the progress of the closeout efforts since February 2002.

# BACKGROUND

The Los Angeles County Metropolitan Transportation Authority (MTA) and its predecessor organizations awarded various facilities, systems, and professional services contracts over a period from the mid-1980’s through 2000.  Work under these contracts was completed but many were not closed out owing to staff reductions and reassignments.

In May 2001, the closeout team was tasked with closing out all of the Metro Red Line inactive contracts.  Closeout of inactive construction facilities, systems, and professional services contracts has been underway for the past two years and significant progress continues to be made.

In February 2002, a presentation was made to the MTA Board to provide an overview of the closeout efforts, a status on closeout progress, and a closeout plan for the remaining work.  As of this writing, closeout efforts have progressed as follows:

| CONTRACT CATEGORY | OPEN MAY 2001 | OPEN FEBRUARY 2002 | OPEN NOVEMBER 2002 | OVERALL PERCENT COMPLETE |
| --- | --- | --- | --- | --- |
| FACILITIES & SYSTEMS | CONTRACTS: 73 VALUE: $1.3B | CONTRACTS: 17 VALUE: $1.1B | CONTRACTS: 8 VALUE: $215M | 95%* |
| PROFESSIONAL SERVICES | CONTRACTS: 138 VALUE: $1.4B | CONTRACTS: 80 VALUE: $1.34B | CONTRACTS: 27 VALUE: 1.3B | 30%* |

*Overall percentage complete is based on the cumulative number of closeout tasks completed to-date.

NEXT STEPS

Another six facilities and systems contracts are projected to be closed by May 2003 leaving the two contracts that are currently in litigation.

Of the 27 open professional services contracts, the majority are cost type and require closeout audits to arrive at the final contract value.  Currently six audits are underway and additional audits will be requested once the necessary documentation becomes available.  Staff should be able to close these open professional services contracts, with the exception of the four contracts currently in litigation, within three months after receipt of the respective audit reports.

Regular closeout meetings are conducted to actively resolve issues that are impeding closeout progress and to develop necessary closeout strategies.

Staff will provide the next status update by June 2003.

ATTACHMENT

- Presentation on Closeout Status – November 2002

Prepared by:	Thomas Mahoney, Deputy Executive Officer, Procurement

Olga Cervantes, Contract Administration Manager

Dennis S. Mori Interim Executive Officer Construction Project Management

Roger Snoble Chief Executive Officer