Implementation Plan for the FY 98-00 Triennial Audit MTA as the Regional Transportation Planning Entity

| Ref No. | Audit Recommendation | Responsibility Lead/Support | Plan for Progress Implementation Instruments | Implementation Date |
| --- | --- | --- | --- | --- |
| 1 | Provide means to identify implications for Board Policy of agenda items where there are alternate points of view within the agency | Joanne Kawai | Management routinely reviews the monthly Board reports to ensure that all viewpoints within the agency have been included. | Complete |
| 2 | Assign specific Procurement personnel to CWP&D to expedite RFP and contract award processes | Lonnie Mitchell | Gary Katzman has been assigned as CA, to begin action on a series of planning bench contracts. RFP will be issued in March 02 with contract award scheduled for Jul 02. | Modeling Bench contracts will be completed by October 2002, Survey Bench contracts by November 2002, and the A&E Bench by February 2003 |
| 3 | Develop a short-term transit operations plan | Rod Goldman | Staff routinely manages the available resources to maximize service. Twice yearly teams are formed to study options and alternatives. We are currently looking forward to changes for the Gold Line and SFV BRT, implementation of 3 new rapid bus lines, and other modifications generated by operators, reallocation requirements, or by the general public. A plan covering June 2002 is in process. | 6/30/02 and then on a 6-month schedule. |
| 4 | Develop a branding specification for Rapid Bus | Rex Gephart | Metro Rapid Program design elements are summarized in a recently published report titled, “Draft Design Criteria for Metro Rapid Bus Transit Facilities on Public Streets and Boulevards”, December 2001. The Program’s five branding principles are discussed in the report. Branding “specifications” will be developed in a separate report. | Complete – Design Element Report. November 2002 – Design/ Specification Report |
| 5 | Implement refinements to the MAP process | Carolyn Flowers | In the FY02, strategic and financial planning responsibilities were consolidated into the Office of Management and Budget department. A new quarterly reporting format was implemented which included a data warehouse with a data dictionary of performance indicators. The quarterly reporting process merged aspects of the prior MAP review process to provide a more cohesive and results oriented process towards linking the agency wide goals and objectives to the financial and strategic planning processes. | Complete |
| 6 | Implement the Long Range Transportation Plan | Brad McAllester | Development of SRTP as an implementation tool for the LRTP has started. The SRTP is anticipated to be complete by June 2003. | June, 2003 |
| 7 | View and analyze corridor projects as an integrated system to identify future improvement needs | Jim de la Loza/ Carol Inge | This will be part of the scope of work for the Short Range Transportation Plan | June, 2003 |
| 8 | Establish a countywide transportation performance reporting program | Jim de la Loza/Brad McAllester /Rod Goldman | The Countywide Transportation Performance Measurement Program will be developed as part of the Regional Short Range Transportation Plan. The RSRTP development has started. | June, 2002 |
| 9 | Implement administrative actions to strengthen and improve compliance with PUC requirements | Jim de la Loza Nalini Ahuja Rufus Cayetano | This recommendation will get implemented as part of recommendation 11. As the fund administration role is strengthened and adequate resources allocated, compliance with PUC requirements will get strengthened. Staff will pay special attention to strengthen this area. However, one of the findings of noncompliance states that fund apportionments be approved by the Board by March 1, which requires that the revenue projections be finalized by January. Given that the MTA Board approves the budget in May/June, revenue estimates get finalized by February/March. The funding estimates therefore get reviewed by the MTA Board in May/June. Given the current MTA process time lines, this recommendation is not realistic. Staff will work with Government Relations and the state to review this requirement. | June, 2002 and then ongoing |
| 10 | Streamline fund administration and improve information available to management and claimants | Jim de la Loza Rufus Cayetano Josie Nicasio | Countywide Planning transit operators and the Accounting department will review the fund administering, invoicing, and reporting procedures to ensure timely and accurate processing of payments. | Complete |
| 11 | Reallocate adequate staff resources to administer funds, develop a countywide SRTP, and collect and report performance information | Jim de la Loza | A reorganization of the Countywide Planning department is currently underway. Adequate staff is being assigned to ensure timely and efficient implementation of functions relating to administering funds, data development and collection. | June, 2002 and ongoing |
| 12 | Review routes of regional significance annually and recommend updates | Rex Gephart/Rod Goldman | Pending February 2002 Board approval of the Metro Rapid Expansion Program, the initial list of Tier One/Metro Rapid corridors will be established. A five-Year Implementation Plan will subsequently be developed which reviews each corridor and establishes an implementation strategy and schedule. An update of each corridor’s transit potential will be made as corridor’s enter the planning and development phase of the Tier One/Metro Rapid Program. | Complete – Approval of Metro Rapid Expansion Program Complete- Five-Year Implementation Plan. As scheduled- Update of corridor transit potential |