## Attach C -Ext List0070803
ATTACHMENT C
LOS ANGELES COUNTY METROPOLITAN TRANSPORTATION AUTHORITY
2003 CALL FOR PROJECTS RECERTIFICATION AND DEOBLIGATION
PROJECTS REQUIRING EXTENSIONS
FY 1991-92 - FY 1999-00
Mode Category
1-Freeway - HOV, TSM and Gap Closures | [8 empty] | 5-Transit Security |  |  | 5-Transit Security
2-Regional Surface Transportation Improvements | [8 empty] | 6-Signal Synchronization and Bus Speed Improvements |  |  | 6-Signal Synchronization and Bus Speed Improvements
3-Transit Capital | [8 empty] | 7-Bikeways and Pedestrian Improvements |  |  | 7-Bikeways and Pedestrian Improvements
4-Transportation Enhancements | [8 empty] | 8-Transportation Demand Management |  |  | 8-Transportation Demand Management
($000)
AGENCY | PROJ NO. | MODE |  | FUND TYPE | 1ST YR OF PRG | PR0JECT TITLE | DOLLARS PROGRAMMED AND FISCAL YEAR | [12 empty] | Funds Subject to Lapsing 06/30/03 | TIME EXTENSION (# YEARS) | [6 empty] | NEW LAPSE DATE JUNE 30, 20XX
|  |  | RTE |  |  |  | 92-98 | 99 | 00 | 01 | FP Total | LOCAL | FEDERAL | STATE | TOTAL | FIS | FED OB | STATE ALLOC | TOTAL |  |  | AREA TEAM | MOU/ LOA/ LNP EXECUTED | Priority Ranking | Prev Ext. Board Date | Ext YR | Need Ext. Y/N |  | COMMENTS
CALTRANS | 2212 | 2 | 14 | RSTP | 1996 | AVENUE P-8, SR-14 (ANTELOPE VALLEY FWY.) TO 50TH ST. EAST (ALSO SEE PROJECT #8021) | 3540 |  |  |  | 3540 | 0 | 3540.3 | 0 | 3540.3 |  | 0 | 0 | 0 | 3540.3 | 2 | SFV/NC | Y | 2 | 37098 | 03 | Y | 05 | Funds are for ROW only.Construction slated to commence Summer 2003. Env. complete. Preparing ROW maps.
CALTRANS | 6380 | 2 | 138 | RIP | 2000 | RTE. 138 RESTRIPING & WIDENING (EA 07-12043) |  |  | 1261 |  | 1261 | 0 | 0 | 1261 | 1261 |  | 0 | 826 | 826 | 435 | 1 | SFV/NC | Y | 3 |  |  | Y | 04 | Construction nearing completion.
GLENDALE | 2401 | 6 |  | PC25 | 1996 | ARROYO VERDUGO TRANSIT PRIORITY SYSTEM & STOP IMPROVEMENTS | 1068 | [7 empty] | 1068 |  |  |  |  | 834 | 2 | [6 empty] | 05
HAWTHORNE | 444179 | 6 |  | PC25 | 1994 | ROSECRANS/AVIATION BRIDGE AND ROADWAY WIDENING | 5700 |  |  |  | 5700 | 5700 | 0 | 0 | 5700 | 4604 | 0 |  | 4604 | 1096 | 1 | SB | Y | 3 | 2001-07-26 | 03 | Y | 04 | design complete; contract in place for Chevron to relocate pipeline as first phase of construction; ext. granted by Jim de la Loza per March 03 memo.
HAWTHORNE | 576 | 2 |  | RSTP | 1994 | ROSECRANS/AVIATION INTERSECTION WIDENING (PH. II) | 2585 |  |  |  | 2585 | 0 | 2585 |  | 2585 |  | 0 | 335 |  | 2585 | 1 | SB | Y | 3 | 2001-07-26 | 03 | Y | 04 | design complete; contract in place for Chevron to relocate pipeline as first phase of construction; ext. granted by Jim de la Loza per March 03 memo.
LA CITY | 2116 | 6 |  | PC25 | 1996 | VAN NUYS BOULEVARD TRANSIT PRIORITY TREATMENTS | 1056 |  |  |  | 1056 | 1056 | 0 | 0 | 1056 | 211.5204 | 0 |  | 211.5204 | 844.4796 | 1 | TP | Y | 1 | 2001-07-26 | 03 | Y | 04 | The project covers transit priority system for the Metro Rapid Program; the project was delayed pending Sep. 2002 MTA Board approval of Metro Rapid Implementation Plan.
LA CITY | 2120 | 6 |  | PC25 | 1996 | GLENDALE BLVD. CORRIDOR IMPROVEMENT PROJECT | 2336 | 861 |  |  | 3197 | 3197 | 0 | 0 | 3197 | 482.8242 | 0 |  | 482.8242 | 2714.1758 | 1 | Central | Y | 3 | 2001-07-26 | 03 | Y | 04 | Under construction
LA CITY | 2121 | 6 |  | PC25 | 1996 | VICTORY/OXNARD BUS PRIORITY TREATMENTS | 2036 |  |  |  | 2036 | 2036 | 0 | 0 | 2036 | 399.9459 | 0 |  | 399.9459 | 1636.0541 | 1 | TP | Y | 1 | 2001-07-26 | 03 | Y | 04 | The project covers transit priority system for the Metro Rapid Program; the project was delayed pending Sep. 2002 MTA Board approval of Metro Rapid Implementation Plan.
LA CITY | 4153 | 3 |  | PC10 | 1998 | WILSHIRE/WESTERN TRANSIT CENTER | 2500 | 721 | [6 empty] | 3221 |  |  |  |  | 2000 | 2 | [6 empty] | 05
LA CITY | 4159 | 3 |  | PC10 | 1998 | WARNER CENTER TRANSIT HUB | 850 | 1200 | [6 empty] | 2050 |  |  |  |  | 2050 | 2 | [6 empty] | 05
LA CITY | 2104 | 6 |  | PC25 | 1998 | WESTSIDE BUS SPEED IMPROVEMENT PROJECT | 3610 |  |  |  | 3610 | 3610 | 0 | 0 | 3610 | 2985.1904 | 0 |  | 2985.1904 | 624.8096 | 1 | TP | Y | 1 | 2001-07-26 | 03 | Y | 04 | The project covers transit priority system for the Metro Rapid Program; the project was delayed pending Sep. 2002 MTA Board approval of Metro Rapid Implementation Plan.
LA CITY | 4193 | 3 |  | PC10 | 1998 | TRANSIT CENTERS | 1591 |  |  |  | 1591 | 1591 | 0 | 0 | 1591 | 1003.4933 | 0 |  | 1003.4933 | 587.5067 | 1 | Transit | Y | 1 |  |  | Y | 04 | An ext. to 04 was given through amendment.
LA CITY | 4058 | 8 |  | PC25 | 1999 | EXPOSITION PARK COMPLEX BICYCLE PARKING PROJECT |  | 41 |  |  | 41 | 41 | 0 | 0 | 41 | 0.001 | 0 |  | 0.001 | 40.999 | 1 | Central | Y | 2 |  |  | Y | 04 | Under construction
LA CITY | 4326 | 2 |  | PC25 | 1999 | MASON AVE. AT-GRADE CROSSING AT S.P.R.R. |  | 261 | 174 |  | 435 | 435 | 0 | 0 | 435 | 413.252 | 0 |  | 413.252 | 21.748 | 1 | SFV/NC | Y | 2 | 2002-06-20 | 03 | Y | 04 | project nearly complete; Const. Phase II begins 5/20/03 which will exhaust remaining funds.
LA CITY | 4068 | 8 |  | PC25 | 1999 | TRIP INFORMATION ELECTRONIC KIOSK AT TRANSIT CENTERS |  | 100 | [6 empty] | 100 |  |  |  |  | 100 | 6M0'S | [6 empty] | 12/31/03
LA CITY | 4248 | 2 |  | PC25 | 2000 | LA CIENGA BLVD. BETWEEN THIRD ST. AND SAN VINCENTE BLVD. |  |  | 42 | 105 |  |  |  |  | 147 |  |  |  |  | 26 | 1 | Central | Y | 3 | 2001-07-26 | 03 | Y | 04
LA CITY | 4313 | 2 |  | PC25 | 2000 | SEPULVEDA BLVD/I - 105 WESTBOUND OFF-RAMP WIDENING |  |  |  | 579 |  |  |  |  | 2340 |  |  |  |  | 579 | 2 | SB | Y | 4 | 2001-07-26 | 03 | Y | 05
LA CITY | 6105 | 8 | LA CITY | PC25 | 2000 | DOWNTOWN WAYFINDING/TRANSIT CONNECTION PROGRAM |  |  | 313 | 261 | 574 | 574 |  |  | 574 |  | 329 | PROJECT LAPSED | 574 | 329 | 1 | CENTRAL | ` |  |  |  |  | 04
LA CITY | 6205 | 4 |  | PC10 | 2000 | LANKERSHIM SOUTHERN PACIFIC RAILROAD STA. REHAB |  |  | 197 | 620 | 817 | 817 | 0 | 0 | 817 | 0 | 0 |  | 0 | 817 | 1 | SFV/NC | Y | 2 | 2002-06-20 | 03 | Y | 04 | Construction contract to be awarded 7-03; one year construction period. Delays by MTA staff for design changes to E/W Rapidway including bus operator restroom.
LA CITY | 6206 | 4 |  | LTF | 2000 | CHATSWORTH HISTORIC TRANS. AND MOVIE MUSEUM |  |  | 52 |  | 52 | 52 | 0 | 0 | 52 | 11.04 | 0 |  | 11.04 | 40.96 | 1 | SFV/NC | Y | 1 | 2002-06-20 | 03 | Y | 04 | In construction.
LA CITY | 6416 | 7 |  | PC25 | 2000 | VERMONT AVE. SIDEWALK WIDENING AND TRANSIT AVENIDA |  |  | 1200 |  | 1200 | 1689 | 0 | 0 | 1689 | 1111.2075 | 0 |  | 1111.2075 | 577.7925 | 1 | Central | Y | 1 | 2002-06-20 | 03 | Y | 04 | Under construction
LA CITY DOT | 2100 | 6 |  | PC25 | 1996 | HARBOR TRANSITWAY ARTERIAL HOV CONNECTION W/DOWNTOWN LA | 4124 |  |  |  | 4124 | 4124 | 0 | 0 | 4124 | 2287.0573 | 0 |  | 2287.0573 | 1836.9427 | 1 | Central | Y | 1 | 2001-07-26 | 03 | Y | 04 | Under construction; one yr. delay due to 9/11 street closure
LA COUNTY | 2214 | 6 |  | PC25 | 1999 | PACIFIC COAST HIGHWAY TRAFFIC MANAGEMENT SYSTEM | 2599 | 2744 | [6 empty] | 5343 |  |  |  |  | 5064 | 2 | [6 empty] | 05
LA COUNTY | 2322 | 7 |  | CMAQ | 1994 | THOMPSON CREEK BICYCLE TRAIL (&623) | 614 |  |  |  | 614 | 181 | 614.1415 | 0 | 795.1415 | 181 | 361.91 |  | 542.91 | 252.2315 | 1 | SGV | Y | 1 |  |  | Y | 04 | under construction; need additional 4 mos. to complete.
LA COUNTY | 2314 | 6 |  | PC25 | 1996 | EAST SAN GABRIEL VALLEY SOM PILOT PROJECT | 7831 |  |  |  | 7831 | 7831 | 0 | 0 | 7831 | 1228.6848 | 0 |  | 1228.6848 | 6602.3152 | 2 | SB | Y | 1 | 2001-07-26 | 03 | Y | 05 | Construction 35% complete; this is the only Signal Forum project not granted an extension to 05 in 2002; this project expands the County's IEN.
LA COUNTY | 2317 | 6 |  | PC25 | 1996 | LOS ANGELES COUNTY TRAFFIC MANAGEMENT CENTER (TMC) | 1344 |  |  |  | 1344 | 1344 | 0 | 0 | 1344 | 347.4357 | 0 |  | 347.4357 | 996.5643 | 2 | SB | Y | 3 | 2001-07-26 | 03 | Y | 05 | Design is complete; staff is currently being relocated to allow for construction; this project is called out in the Draft SRTP.
LONG BEACH | 231602 | 2 |  | PC25 | 1996 | ARTERIAL HOV | 5125 | [7 empty] | 5125 |  |  |  |  | 3500 | 2 | [6 empty] | 05
LONG BEACH | 4084 | 7 | LONG BEACH | TEA | 2000 | BEACH BIKE PATH REALIGNMENT AT BELMONT PIER |  | 200 | [6 empty] | 200 |  |  | 200 | 0 | 200 | 1 | 200 | 1 | SB | Y | 4 | 37098 | 04 | Y
MTA | 2445 | 3 |  | PC10 | 1996 | WESTLAKE COMMUNITY BASED INTERCEPT INTERMODAL FACILITY | 2600 | [7 empty] | 2600 |  |  |  |  | 2600 | 2 | [6 empty] | 05
MTA | 4295 | 3 |  | PC10 | 2000 | WESTLAKE COMMUNITY BASED INTERCEPT INTERMODAL FACILITY |  |  | 1700 | [5 empty] | 1700 |  |  |  |  | 1400 | 2 | [6 empty] | 05
MTA | 2250 | 6 |  | PC25 | 1996 | MTA BUS PRIORITY SYSTEM PILOT PROJECT AND IMPLEMENTATION | 4819 |  |  |  | 4819 | 4819 | 0 | 0 | 4819 |  | 0 |  | 0 | 4819 | 1 | SGV | N/A | 1 | 2001-07-26 | 03 | Y | 04 | Under construction; need one yr ext. due to Metro Rapid coordination along Crenshaw Blvd.
MTA | 2080 | 7 |  | TEA | 1999 | EXPOSITION BOULEVARD RIGHT-OF-WAY BIKEWAY PHASE I | 275 | [6 empty] | 275 | 0 | 275 | 0 | 275 | 0 | 275 | 1 | 275 | 1 | Westside | N/A | 3 |  | 04 | Y
MTA | 4094 | 7 |  | RSTP | 2000 | EL PUEBLO PED IMPROV./GENERAL ANGELS' WALK IMPROV. |  |  | 1342 | 404 | 1746 | 1746 | 0 | 0 | 1746 | 1000 | 0 |  | 1000 | 746 | 1 | Central | Y | 1 | 2002-06-20 | 03 | Y | 04 | Under construction; County's portion in design; City's portion complete
MTA | 4227 | 6 |  | PC25 | 2000 | LOS ANGELES/VENTURA REGIONAL ADVANCED TRAVELER INFO. SYS. |  |  | 438 |  | 438 | 438 | 1260 | 0 | 1698 |  | 1157 |  | 1157 | 541 | 1 | Gateway | N/A | 1 | 2002-06-20 | 03 | Y | 04 | Proj. 90% complete as of 3/03
MTA | 4235 | 6 |  | PC25 | 2000 | SIGNAL SYSTEM TECHNICIAN TRAINING PROGRAM |  |  | 133 | 136 | 269 | 269 | 0 | 0 | 269 | 62.919 | 0 |  | 62.919 | 206.081 | 1 | Countywide | Y | 1 |  |  | Y | 04 | training workshops have been scheduled and committed for FY 04. Funds budgeted by HRODT in FY 04.
PALMDALE | 6087 | 2 |  | LTF | 2000 | ROUTE 138 (AVENUE P8) RIGHT-OF-WAY ACQUISITION (SEE PROJECT 2212-local match to RSTP funds) |  |  | 32 | 12 | 44 | 44 | 0 | 0 | 44 |  | 0 |  | 0 | 44 | 2 | SFV/NC | Y | 2 |  | Dec. 03 |  | 05 | Local match to Proj. 2212 SRTP funds; ROW only
REDONDO BEACH | 4087 | 7 |  | TEA | 2000 | REDONDO BEACH PORTION OF THE BAY CITIES REGIONAL BIKEWAY |  |  | 806 | [5 empty] | 806 |  |  |  |  | 742 | 1 | SB | Y | 4 | 2001-07-26 | 03 | Y | 04
SGV COG | 4367LK | 2 |  | PC25 | 1999 | ALAMEDA CORRIDOR EAST - GATEWAY TO AMERICA (LINK WITH PROJECT #4423) |  | 4000 | 9004 |  | 13004 | 14140 | 0 | 0 | 14140 |  | 0 | 0 | 0 | 5000 | 2 | SGV | Y | 1 | 2002-06-20 | 03 | Y | 05 | Under construction
SOUTH BAY JPA | 2343 | 2 |  | PC25 | 1996 | AVIATION BLVD./MANHATTAN BCH BLVD. TO ARBOR VITAE ST. | 6002 |  |  |  | 6002 | 6002 | 0 | 0 | 6002 | 200 | 0 | 0 | 200 | 5802 | 1 | SB | Y | 4 | 2001-07-26 | 03 | Y | 04 | design complete; contract in place for Chevron to relocate pipeline as first phase of construction; ext. granted by Jim de la Loza per March 03 memo.
WEST HOLLYWOOD | 6063 | 3 |  | PC10 | 2001 | SANTA MONICA BUS FACILITY |  |  | 62 | [5 empty] | 62 |  |  |  |  | 62 | 6M0'S | [6 empty] | 12/31/03
ready to list
[6 empty] | TOTAL | 62205 | 10128 | 16756 | 2117 | 67930 | 61736 | 7999.4415 | 1536 | 95758.4415 | 16804.5715 | 1847.91 | 1636 | 19448.4815 | 62168.96