## Expo Cashflow
Los Angeles County Metropolitan Transportation Authority
Mid-City/Exposition Transit Corridor -- Escalated Capital Costs Cashflow -- Planning Estimate
Revenue Operation Date: Sept 2012 (potential advancement to FY2010 is being reviewed -- see report text)
(in millions of dollars escalated to the year of expenditure) | [5 empty] | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA
Uses of Funds |  | Total 2003$ | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015 | Total | % of Total
Construction and Procurement
| Guideways | 54.7 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 9.2; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 8.2; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 11.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 18.3; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 13.3; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 5.1 | 66 | 13.48%
| Yards and Shops | 20.3 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 1.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 1.2; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 3.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 5.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 12.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 1.3 | 24.9 | 5.085%
| Systems | 63.9 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 2.3; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 16.7; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 20.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 31.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 7.6 | 78.3 | 15.99%
| Stations | 20.8 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 1.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 4.8; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 6.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 10.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 2.5 | 25.4 | 5.187%
| Vehicles (16) | 50.8 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 20.3; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 41.1 | 61.4 | 12.54%
| Special Conditions | 41.6 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 8; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 7.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 7.2; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 13.4; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 7.5; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 7 | 50.2 | 10.25%
| Right-of-Way | 16.6 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 4.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 14.7 | 19.3 | 3.941%
Subtotal Construction and Procurement |  | 268.7 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 33.5 | 64 | 104.6 | 75.9 | 23.5 | 0 | 325.5 | 66.47%
Professional Services |  | 72.1 | 3 | 8.3 | 8.4 | 6.5 | 5.5 | 4.5 | 7.4 | 8.9 | 9.5 | 9.7 | 5 | 5.1 |  | 81.8 | 16.7%
Project Contingency |  | 67.3 | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 11.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 14.3; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 15.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 14.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 25.4 | 82.4 | 16.83%
Total Project Cost |  | 408.1 | 3 | 8.3 | 8.4 | 6.5 | 5.5 | 4.5 | 31.4 | 54.3 | 87.8 | 130.2 | 95.8 | 54 | 0 | 489.7 | 100%
Interest Cost |  |  | 0 | 0 | 0.5 | 0.8 | 1.2 | 1.4 | 1.5 | 1.6 | 1.8 | 2.1 | 2.5 | 2.4 | 0 | 15.8
Total Cost |  |  | 3 | 8.3 | 8.9 | 7.3 | 6.7 | 5.9 | 32.9 | 55.9 | 89.6 | 132.3 | 98.3 | 56.4 | 0 | 505.5
Sources of Funds
| Prop A 35% | [14 empty] | 0 | 0%
| Prop C 25% |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2008: 0.2; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2009: 31.4; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 15.9; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 55.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 21.7; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 3.1; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2015: 39.8 | 167.7 | 33.18% | 167.7 | 33.18%
| Other Local (ROW Contribution) | [14 empty] | 0 | 0% |  | 0%
| CMAQ |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2015: 7.9 | 7.9 | 1.563% | 7.9 | 1.563%
| RSTP |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 2 | 2 | 0.3956% | 2 | 0.3956%
| 5309 Fixed Guideway Modernization | [14 empty] | 0 | 0% |  | 0%
| 5309 New Starts |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 22.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2011: 70; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2012: 70; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2013: 70; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 20.1 | 252.7 | 49.99% | 252.7 | 49.99%
| Traffic Congestion Relief Prog (TCRP) |  | FY 2003: 3; FY 2004: 8 | 11 | 2.176% | 11 | 2.176%
| State Regional Improvement Program |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2010: 31.6; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: 32.6 | 64.2 | 12.7% | 64.2 | 12.7%
Total Sources |  |  | 3 | 8 | 0 | 0 | 0 | 0.2 | 31.4 | 54.2 | 85.9 | 125.6 | 91.7 | 57.8 | 47.7 | 505.5 | 100% | 505.5 | 100%
Surplus/(Deficit) before Bridge Loan |  |  | 0 | -0.3 | -8.4 | -6.5 | -5.5 | -4.3 | 0 | -0.1 | -1.9 | -4.6 | -4.1 | 3.8 | 47.7 | 15.8
Gross Bridge Loan Proceeds |  |  |  | 0.3 | 8.9 | 7.3 | 6.7 | 5.7 | 1.5 | 1.7 | 3.7 | 6.7 | 6.6 |  |  | 49.1
Bridge Loan Principal Payment |  |  | AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2014: -1.4; AT-GRADE EXCEPT FOR AN AERIAL STATION AT LA CIENEGA FY 2015: -47.7 | -49.1
Bridge Loan Principal Balance |  |  |  | 0.3 | 9.2 | 16.5 | 23.2 | 28.9 | 30.4 | 32.1 | 35.8 | 42.5 | 49.1 | 47.7 | 0
Interest (5%) |  |  |  | 0 | -0.5 | -0.8 | -1.2 | -1.4 | -1.5 | -1.6 | -1.8 | -2.1 | -2.5 | -2.4 | 0 | -15.8
Net Surplus/(Deficit) after Bridge Loan |  |  |  | -7.2164e-16 | 0 | 0 | 0 | 0 | 0 | 5.5511e-15 | 8.6597e-15 | -2.2649e-14 | -8.8818e-15 | 4.4409e-15 | -7.1054e-15
Notes:
1. "Special Conditions" includes Utility relocation, environmental, master cooperative agreements, OCIP, testing, artwork, ATCS costs, Neighborhood Mitigation, etc.
2. "Professional Services" includes Engineering, Construction Management, Agency & Specialty Consultants
3. Bridge loans may not be necessary if other local funds can be substituted based on final audits and available funds.
4. If all or part of the $238.8 million of suspended TCRP funding becomes available for allocation, replacement of the local funds may be considered.